## Users
Email | Name | Role
hussain@company.com | Hussain | Maintenance Manager

## Sites
SiteID | SiteName | Region | Status
SITE001 | Uqlat Al Soqour | Qassim | Active
SITE002 | Al Hadar | WD | Active | 0 | 0
SITE003 | Al Hulifa | Madina | Active | 0 | 0
SITE004 | Al Sabiyah | Madina | Active | 0 | 0
SITE005 | WB | Al Baha | Active | 0 | 0

## Data
WO No | Site | Area | Category | Priority | Description | Assigned To | Status | Reported Date | Completion Date | Final Cost | Parts Used |  |  | Closing Notes
WO0001 | Uqlat Al Soqour | Qassim | Carpentry | High | Caravan Floor Broken (GYM) | Hussein | Closed | 2026-07-02 | 2026-07-18 16:09 | 0 |  |  |  | good condition
WO0002 | Uqlat Al Soqour | Qassim | Plumbing | High | Pump pipe / Pump discharge pipe | Hussein | Closed | 2026-07-03 | 2026-07-19 16:37 | 0 |  |  |  | change by employee
WO0003 | Uqlat Al Soqour | Qassim | Plumbing | High | spray with hose 5 Pcs with 4 bathroom | Hussein | Closed | 2026-07-04 | 2026-07-05 15:34 | 0 |  |  |  | Repair the Toilet spray
WO0004 | Uqlat Al Soqour | Qassim | Carpentry | High | Security Door (Caravan ) | Hussein | Closed | 2026-07-04 | 2026-07-05 15:32 | 0 |  |  |  | Door hinge holes were repaired
WO0005 | Uqlat Al Soqour | Qassim | Other | Medium | Door Lock Room Nu (2) | Hussein | Closed | 2026-07-05 | 2026-07-05 15:31 | 0 |  |  |  | Repair ( internal locking mechanism failed)
WO0006 | Uqlat Al Soqour | Qassim | Plumbing | High | Hand Spry Hose 3 Pcs change | Hussein | Closed | 2026-07-05 | 2026-07-18 16:42 | 0 |  |  |  | done
WO-0007 | Al Hadar | WD | HVAC | Urgent | A/C not Working | Contractor | Closed | 2026-07-08 | 2026-07-09 22:40 | 270 |  | Al Jodood | 270 | clean and add feron
WO-0008 | Al Hadar | WD | General | Urgent | Camera (Parking area ) | Amro | Closed | 2026-07-08 | 2026-07-18 19:34 | 0 |  |  |  | fixed
WO-0009 | Uqlat Al Soqour | Qassim | Carpentry | Urgent | Bed QTY 2 | Hussein | Closed | 2026-07-06 | 2026-07-08 18:35 | 0 |  |  |  | repair 2 beds
WO-0010 | Uqlat Al Soqour | Qassim | General | Urgent | Office Wall (Crack ) | Hussein | Closed | 2026-07-08 | 2026-07-08 18:35 | 0 |  |  |  | repair the wall
WO-0011 | Al Hulifa | Madina | General | High | Flush button (Toilet seat) 2 pcs | Noman | Closed | 2026-07-06 | 2026-07-19 15:33 | 0
WO-0012 | Al Sabiyah | Madina | HVAC | Medium | Change pump for desert cooler | Shahzad | Closed | 2026-07-19 16:39 | 2026-07-19 16:41 | 100 |  | Al Jodood | 100 | change the pump now good
WO-0013 | Al Sabiyah | Madina | HVAC | Medium | Clean AC & Washing 3pcs / after that request A/C Split installation | Shahzad | Closed | 2026-07-19 16:46 | 2026-07-19 16:47 | 450 |  | Al Jodood | 450 | clean 3 pcs A/C
WO-0014 | Al Sabiyah | Madina | Electrical | High | Repair Electrical Breaker | Shahzad | Closed | 2026-07-19 16:51 | 2026-07-19 17:00 | 80 |  | Al Jodood | 80 | repair
WO-0015 | Al Sabiyah | Madina | Plumbing | High | Change existing Water pump | Shahzad | Closed | 2026-07-19 17:52 | 2026-07-19 18:10 | 80 |  | Al Jodood | 80 | done change the pump
WO-0016 | Al Hulifa | madina | HVAC | High | Feron for Split AC | Nomaan | Closed | 2026-07-19 18:13 | 2026-07-19 18:15 | 270 |  | Al Jodood | 270 | ready (done)
WO-0017 | Al Hulifa | Madina | Electrical | Medium | Electrical Breaker | Nomaan | Closed | 2026-07-19 18:17 | 2026-07-19 18:19 | 140 |  | Al Jodood | 140 | 140 because they fixed first time as temporary and second time fixed
WO-0018 | Uqlat Al Soqour | Qassim | Electrical | Medium | Cable 3x4mm with Clips - Socket with Box - Condute | Rhys | Closed | 2026-07-19 18:25 | 2026-07-30 21:45 | 0 |  |  | 0 | done
WO-0019 | Al Hulifa | madina | HVAC | High | sensor For A/C window | Nomaan | Closed | 2026-07-29 12:17 | 2026-07-29 12:27 | 0 |  |  |  | done
WO-0020 | Al Hulifa | Madina | General | Medium | Fan | Nomaan | Closed | 2026-07-29 12:18 | 2026-07-29 12:27 | 70 |  | Al Jodood | 70 | done
WO-0021 | Al Hulifa | Madina | General | Medium | Alumninum door lock | nomaan | Closed | 2026-07-29 12:19 | 2026-07-29 12:28 | 70 |  | Al Jodood | 70 | done
WO-0022 | Al Hulifa | Madina | HVAC | High | Feron For A/C - window | nomaan | Closed | 2026-07-29 12:21 | 2026-07-29 12:25 | 150 |  | Al Jodood | 150 | good condition
WO-0023 | Al Sabiyah | Madina | Electrical | Medium | socket | Shahzad | Closed | 2026-07-29 13:25 |  | 0
WO-0024 | Al Sabiyah | madina | Electrical | High | A/C switch | shahzad | Closed | 2026-07-29 13:26 |  | 0
WO-0025 | Al Hadar | WD | Plumbing | High | Kitchen waste pipe repair | Mostafa | Closed | 2026-07-29 13:37 | 2026-07-29 13:40 | 250 |  | Al Jodood | 250 | The drain was opened, and the rice blockage was removed from inside
WO-0026 | Uqlat Al Soqour | Qassim | Plumbing | Medium | Washbasin faucet | Samer | Closed | 2026-07-29 15:12 | 2026-07-29 15:12 | 0 |  |  |  | replaced new
WO-0027 | Uqlat Al Soqour | Qassim | Plumbing | High | 1 Toilet angle valve | Samer | Closed | 2026-07-29 15:14 |  | 0
WO-0028 | Uqlat Al Soqour | Qassim | Plumbing | Medium | Shower mixer | Samer | Closed | 2026-07-29 15:15 |  | 0
WO-0030 | Uqlat Al Soqour | Qassim | Electrical | Medium | Celling light not working (Bathroom) | Samer | Closed | 2026-07-30 18:52 | 2026-07-30 18:53 | 80 |  | Al Jodood | 80 | done
WO-0031 | Uqlat Al Soqour | Qassim | Electrical | Critical | Socket for Oven | Samer | Closed | 2026-07-30 18:54 | 2026-07-30 18:57 | 50 |  | Al Jodood | 50 | done
WO-0032 | Uqlat Al Soqour | Qassim | Electrical | Medium | Fan | Samer | Closed | 2026-07-30 18:58 | 2026-07-30 19:02 | 60 |  | Al Jodood | 60 | done
WO-0033 | Uqlat Al Soqour | Qassim | General | Medium | Steel has a dust need repaint | Hussam | Closed | 2026-07-30 18:59 | 2026-07-30 19:01 | 50 |  | Al Jodood | 50 | done
WO-0034 | Al Sabiyah | Madina | Mechanical | Medium | Door bolt lock | Shahzad | Closed | 2026-07-30 20:24 | 2026-07-31 14:41 | 0 |  | Al Jodood | 0 | replaced new
WO-0034 | Al Sabiyah | Madina | Plumbing | Medium | Shower head not working | Shahzad | Closed | 2026-07-31 14:36 | 2026-07-31 14:41 | 0 |  |  | 0 | replaced new
WO-0035 | Al Sabiyah | Madina | Plumbing | Medium | spray water (bathroom) not working | Shahzad | Closed | 2026-07-31 14:37 | 2026-07-31 14:40 | 0 |  |  | 0 | replaced new
WO-0036 | Al Hadar | WD | HVAC | Medium | A/C (water drain) | mostafa | Closed | 2026-08-01 11:30 | 2026-08-10 10:47 | 200 |  | Al Jodood | 200 | add feron for 2 pcs
WO-0037 | Al Hadar | WD | Electrical | Medium | Electric plug (security room) 2 pcs | mostafa | Closed | 2026-08-01 11:31 | 2026-08-10 10:30 | 60 |  | Al Jodood | 60 | remove and install new sockets 2 pcs
WO-0038 | Al Hadar | WD | Electrical | High | outside light | mostafa | Closed | 2026-08-01 11:32 | 2026-08-10 10:39 | 70 |  | Al Jodood | 70 | replaced, done
WO-0039 | Al Sabiyah | Madina | Electrical | Medium | Stainless Steel Flying Insect Killer Machine(light not working) 3pcs | Shahzad | Closed | 2026-08-02 10:25 | 2026-08-10 10:20 | 0 |  |  | 0 | fixed, done
WO-0040 | Al Sabiyah | Madina | Electrical | Medium | DVR (Digital Video Recorder) Fan | Shahzad | Closed | 2026-08-02 10:33 | 2026-08-02 10:33 | 0 |  |  | 0 | clean the fan and fixed
WO-0041 | Uqlat Al Soqour | Qassim | General | High | Ceramic Tiles | Samer | Closed | 2026-08-02 10:39 | 2026-08-15 07:47 | 160 |  | Al Jodood | 160 | repair done
WO-0042 | Uqlat Al Soqour | Qassim | Plumbing | Medium | handheld spray | samer | Closed | 2026-08-09 07:28 | 2026-08-11 07:12 | 0 |  |  | 0 | replaced
WO-0043 | Uqlat Al Soqour | Qassim | Plumbing | Medium | handheld spray | samer | Closed | 2026-08-09 07:29 | 2026-08-11 07:13 | 0 |  |  | 0 | replace
WO-0044 | Uqlat Al Soqour | Qassim | General | Medium | Door handle (wood) | samer | Open | 2026-08-09 07:31
WO-0045 | Al Hulifa | Madina | General | High | The water doesn't go down the drain | nomaan | Closed | 2026-08-02 07:31 | 2026-08-13 09:15 | 170 |  | Al Jodood | 170 | done
WO-0046 | Uqlat Al Soqour | Qassim | Electrical | Medium | Fan | samer | Closed | 2026-08-09 07:32 | 2026-08-10 10:50 | 35 |  | Al Jodood | 35 | replaced
WO-0047 | Uqlat Al Soqour | Qassim | Plumbing | Medium | mixer connection | samer | Closed | 2026-08-09 07:33 | 2026-08-10 10:52 | 35 |  | Al Jodood | 35 | install new mixer
WO-0048 | Uqlat Al Soqour | Qassim | General | Medium | toilet seat cover (crack bolt) | samer | Closed | 2026-08-09 07:35 | 2026-08-11 07:19 | 0 |  | Al Jodood | 0 | fixed
WO-0049 | Uqlat Al Soqour | Qassim | Plumbing | Medium | There Is no water in the bathroom | samer | Closed | 2026-08-09 07:36 | 2026-08-11 07:21 | 0 |  | Al Jodood | 0 | repair
WO-0050 | Uqlat Al Soqour | Qassim | Plumbing | Medium | no water hoses | samer | Closed | 2026-08-09 07:39 | 2026-08-11 07:11 | 0 |  |  | 0 | install new hose
WO-0051 | Uqlat Al Soqour | Qassim | Plumbing | Medium | handle shower leaking | samer | Closed | 2026-08-09 07:40 | 2026-08-11 07:16 | 0 |  |  | 0 | relace
WO-0052 | Al Hulifa | Madina | General | Medium | the water in the bathroom unlevel (caravan ) all bathroom | Nomaan | Closed | 2026-08-09 08:39 | 2026-08-15 09:02 | 600 |  | Al Jodood | 600 | done
WO-0053 | Al Hulifa | Madina | Plumbing | Medium | hot water not working | nomaan | Closed | 2026-08-09 08:41 | 2026-08-15 08:39 | 115 |  | Al Jodood | 115 | testing water heater with mixer
WO-0054 | Al Hadar | WD | Electrical | Medium | light not working 3 pcs | Amro | Closed | 2026-08-09 08:44 | 2026-08-21 16:52 | 136 |  | Al Jodood | 136 | change 8 pcs
WO-0055 | Al Hadar | WD | HVAC | Medium | A/C not working | Amro | Closed | 2026-08-09 08:46 | 2026-08-13 09:25 | 300 |  | Al Jodood | 300 | adda feron
WO-0056 | Al Hulifa | Madina | Plumbing | Medium | spray water (bathroom) not working | Nomaan | Closed | 2026-08-10 10:16 | 2026-08-10 10:17 | 0 |  |  | 0 | our employee fixed (cleaner)
WO-0057 | Uqlat Al Soqour | Qassim | Electrical | Medium | light not working | samer | Closed | 2026-08-10 10:57 | 2026-08-10 10:59 | 35 |  | Al Jodood | 35 | install new light
WO-0058 | Uqlat Al Soqour | Qassim | Electrical | Medium | A/C Switch not working | samer | Closed | 2026-08-10 11:00 | 2026-08-10 11:01 | 35 |  | Al Jodood | 35 | install new switch
WO-0059 | Al Hulifa | Madina | Plumbing | Medium | water flashing for toilet leaking | Nomaan | Closed | 2026-08-10 11:08 | 2026-08-10 11:10 | 75 |  | Al Jodood | 75 | install new
WO-0060 | Al Sabiyah | Madina | Electrical | Medium | light 3 pcs not working | Shahzad | Closed | 2026-08-10 11:16 | 2026-08-10 11:17 | 0 |  |  | 0 | change new light 3 pcs
WO-0061 | Wadi Beddah | Al Baha | Plumbing | Medium | handle spray | meshal | Closed | 2026-08-13 07:24 | 2026-08-13 07:39 | 690 |  | Raghad Al OFQ | 690 | done closed in july
WO-0062 | Wadi Beddah | Al Baha | Plumbing | Medium | handle shower | meshal | Closed | 2026-08-13 07:25 | 2026-08-13 07:40 | 0 |  | Raghad Al OFQ | 0 | done, closed in july
WO-0063 | Wadi Beddah | Al Baha | Electrical | Medium | Light (out side) 100 wat | meshal | Closed | 2026-08-13 07:26 | 2026-08-13 07:41 | 0 |  | Raghad Al OFQ | 0 | done, closed in july
WO-0064 | Wadi Beddah | Al Bahah | Electrical | Medium | spot light 20 | meshal | Closed | 2026-08-13 07:28 | 2026-08-13 07:41 | 0 |  | Raghad Al OFQ | 0 | done, closed in july
WO-0065 | Wadi Beddah | Al Baha | Electrical | Medium | spot light 8 | meshal | Closed | 2026-08-13 07:29 | 2026-08-13 07:42 | 0 |  | Raghad Al OFQ | 0 | done, closed in july
WO-0066 | Wadi Beddah | Al Baha | Plumbing | Medium | Drain trap | Meshal | Closed | 2026-08-13 07:30 | 2026-08-13 07:43 | 0 |  | Raghad Al OFQ | 0 | done, closed in july
WO-0067 | Wadi Beddah | Al Baha | General | Medium | Door Handle | meshal | Closed | 2026-08-13 07:32 | 2026-08-13 07:44 | 0 |  | Raghad Al OFQ | 0 | done, closed in july
WO-0068 | Wadi Beddah | Al Baha | Electrical | Medium | fan 30*30 | meshal | Closed | 2026-08-13 07:32 | 2026-08-13 07:44 | 0 |  | Raghad Al OFQ | 0 | done, closed in july
WO-0069 | Uqlat Al Soqour | Qassim | Electrical | Medium | fan not working | samer | Closed | 2026-08-15 14:36 | 2026-08-27 14:58 | 0 |  | Al Jodood | 0
WO-0070 | Uqlat Al Soqour | Qassim | General | Medium | handle door | samer | Closed | 2026-08-15 14:38 | 2026-08-27 14:58 | 0 |  | Al Jodood | 0
WO-0071 | Uqlat Al Soqour | Qassim | General | Medium | There is mold on the wall | Husam | Closed | 2026-08-15 14:42 | 2026-08-15 14:43 | 0 |  | company | 0 | clean only
WO-0072 | Al Sabiyah | Madina | General | Medium | There is a crack in the kitchen floor. | Shahzad | Closed | 2026-08-15 14:52 | 2026-08-15 15:07 | 0 |  |  | 0 | fixed and paint
WO-0073 | Al Hadar | WD | Plumbing | Medium | water pump timer | amro | Closed | 2026-08-15 14:55 | 2026-08-15 14:58 | 110 |  | Al Jodood | 110 | replaced, done
WO-0074 | Wadi Beddah | Al Baha | HVAC | Medium | A/C not cooling good | meshal | Closed | 2026-08-15 15:09 | 2026-08-27 11:09 | 450 |  | Raghad Al OFQ | 450
WO-0075 | Al Sabiyah | Madina | General | Medium | core shed door not close and not fixed | max | Closed | 2026-08-18 09:28 | 2026-08-27 11:09 | 150 |  | Al Jodood | 150 | done
WO-0076 | Al Sabiyah | Madina | General | Medium | cutting area door need fixe | max | Closed | 2026-08-18 09:30 | 2026-08-27 11:09 | 150 |  | Al Jodood | 150 | done
WO-0077 | Al Sabiyah | Madina | Plumbing | Medium | shower need fix | shahzad | Closed | 2026-08-18 09:34 | 2026-08-18 09:39 | 0 |  |  | 0 | fixed
WO-0078 | Al Sabiyah | Madina | Electrical | Medium | light not working 3 pcs | shahzad | Closed | 2026-08-18 09:35 | 2026-08-15 14:58 | 0
WO-0079 | Uqlat Al Soqour | qassim | Plumbing | Medium | A water valve handle is damaged, causing continuous water leakage | samer | Closed | 2026-08-20 13:44 | 2026-08-27 14:56 | 100 |  | Al Jodood | 100 | fixed
WO-0080 | Uqlat Al Soqour | Qassim | Plumbing | Medium | There is a water leak in one of the barracks. | samer | Closed | 2026-08-20 13:46 | 2026-08-27 14:58 | 100 |  | Al Jodood | 100 | fixed
WO-0081 | Uqlat Al Soqour | Qassim | Plumbing | Medium | Water from one of the faucets has a persistent unpleasant taste and odor. This issue has been ongoing for some time, and the cause is currently unknown. | samer | Closed | 2026-08-20 13:47 | 2026-08-27 14:58 | 200 |  | Al Jodood | 200 | fixed
WO-0082 | Uqlat Al Soqour | Qassim | Electrical | Medium | Two lights in one room are completely not working. | samer | Closed | 2026-08-20 13:48 | 2026-08-27 14:59 |  |  | Al Jodood |  | done
WO-0083 | Wadi Beddah | Al Baha | HVAC | Medium | A/C store (leaking water) | Meshal | Closed | 2026-08-21 17:03 | 2026-08-27 14:59 | 0 |  | Raghad Al OFQ | 0
WO-0084 | Wadi Beddah | Al Baha | Electrical | Medium | lights long 2 pcs | Meshal | Closed | 2026-08-21 17:14 | 2026-08-27 23:21 | 0 |  | Raghad Al OFQ | 0 | done
WO-0085 | Al Hulifa | Madina | HVAC | Medium | A/C Window 8 pcs | Nouman | Open | 2026-08-21 17:25 |  |  |  | Al Jodood
WO-0086 | Al Hulifa | madina | Plumbing | Medium | shower mixer | Nouman | Closed | 2026-08-27 18:07 | 2026-08-27 18:13 | 24 |  | Al Jodood | 24 | done
WO-0087 | Al Hulifa | madina | Mechanical | Medium | aluminum door hand need repair | Nouman | Closed | 2026-08-27 18:15 | 2026-08-27 18:13 | 92 |  | Al Jodood | 92
WO-0088 | Al Hadar | WD | HVAC | Medium | need washing 3 pcs A/C | Amro | Closed | 2026-08-27 18:19 | 2026-08-27 18:20 | 450 |  | Al Jodood | 450 | clean filter and washing the A/C 3 pcs
WO-0089 | Uqlat Al Soqour | Qassim | Electrical | High | Panel breaker 20 Am burn | samer | Closed | 2026-08-27 18:32 | 2026-08-27 18:36 | 96 |  | Al Jodood | 96 | done
WO-0090 | Wadi Beddah | WB | Electrical | Medium | light size 7 | meshal | Closed | 2026-08-27 22:55 | 2026-08-27 23:27 | 0 |  | Raghad Al OFQ | 0 | done
WO-0091 | Wadi Beddah | WB | Electrical | Medium | light size 20 | meshal | Closed | 2026-08-27 22:57 | 2026-08-27 23:26 | 0 |  | Raghad Al OFQ | 0 | done
WO-0092 | Wadi Beddah | WB | Electrical | Medium | out side light | meshal | Closed | 2026-08-27 22:58 | 2026-08-27 23:25 | 0 |  | Raghad Al OFQ | 0 | done
WO-0093 | Wadi Beddah | WB | Electrical | Medium | Long outdoor LED strip light | meshal | Closed | 2026-08-27 23:00 | 2026-08-27 23:25 | 0 |  | Raghad Al OFQ | 0 | done
WO-0094 | Wadi Beddah | WB | Plumbing | Medium | Arabic toilet flush | meshal | Closed | 2026-08-27 23:02 | 2026-08-27 23:24 | 0 |  | Raghad Al OFQ | 0 | done
WO-0095 | Wadi Beddah | WB | Plumbing | Medium | Angle valve | meshal | Closed | 2026-08-27 23:03 | 2026-08-27 23:23 | 0 |  | Raghad Al OFQ | 0 | done
WO-0096 | Wadi Beddah | WB | Plumbing | Medium | Shower mixer | meshal | Closed | 2026-08-27 23:04 | 2026-08-27 23:22 | 0 |  | Raghad Al OFQ | 0 | done

## SiteTasks
ID | Site Name | Task Description | Start Date | Close Date | Amount | Status | Assigned To | Timestamp
ST-0002 | Al Hadar | camera | 2026-07-10 | 2026-07-18 | 0 | Closed | jodod | 2026-07-10T17:06:29.564Z

## MonthlySavings
Month | Year | Contractor WO | Contractor Dev | Parts WO | Parts Dev | Total Labor | Total Parts | Total Cost | Maintenance Savings | Development Savings | Maintenance % | Development % | Total Savings %
July | 2026 | 2170 | 2525 | 1417 | 3281 | 4695 | 4698 | 9393 | 14840.1417 | 124594.695 | 72.1 | 93.9978 | 91.0578
Aug | 2026 | 4638 | 58406 | 6601 | 0 | 63044 | 6601 | 69645 | 7188.1417 | 74145.695 | 34.9 | 54.3378 | 82.3338

## DevTasks
ID | Project ID | Task Name | Cost | Contractor | Status
TASK-0002 | DEV-0004 | Install a new electrical outlet | 50 | Al Jodood | In Progress

## Parts
ID | WO No | Part Name | Quantity | Unit Price | Total Price
PART001 | WO0001 | Handle spray | 2 | 0 | 0
PART002 | WO0003 | Hinge | 4 | 5 | 20

## ProjectManagement
ID | Location | Description | Start Date | End Date | Status | Total Cost | Contractor Cost | Contractor |  | Image
PRJ001 | Uqlat Al Soqour | A/C not Working ¦ Closed: Done | 2026-07-08 | 2026-07-08 | Closed | 0
PRJ002 | Bir Umq |  |  |  |  | 0
PRJ003 | Al Hulifa |  |  |  |  | 0
PRJ004 | WB |  |  |  |  | 0
PRJ-0005 | Al Hadar |  |  |  |  | 0
PRJ-0006 | Al Sabiyah | Emergency Light including installation ¦ Closed: done | 2026-07-08 | 2026-07-08 | Closed | 210 | 210 | Al Jodood
PRJ-0007 | Al Sabiyah | AC Split installation | 2026-07-08 | 2026-07-08 | Closed | 450 | 450 | Al Jodood
PRJ-0008 | Uqlat Al Soqour | Cable 3x4mm with Clips - Socket with Qassim ¦ Closed: done Box - Condute | 2026-07-10 | 2026-07-10 | Closed | 65 | 65 | Al Jodood | 0 | data:image/jpeg;base64,/9j/4Xc1RXhpZgAATU0AKgAAAAgADgEAAAMAAAABC7gAAAEBAAMAAAABD6AAAAECAAMAAAADAAAA9gEPAAIAAAAHAAAAtgEQAAIAAAAIAAAAvgESAAMAAAABAAAAAAEaAAUAAAABAAAAxgEbAAUAAAABAAAAzgEoAAMAAAABAAIAAAExAAIAAAAgAAAA1gEyAAIAAAAUAAAA/AITAAMAAAABAAEAAIdpAAQAAAABAAABEKQLAAcAAAAEaXBwAAAAIvRIVUFXRUkAAEFRTS1MWDEAAAAASAAAAAEAAABIAAAAAUFRTS1MMjFBIDEyLjAuMC4yMzkoQzE4NUU1UjRQMSkAAAgACAAIMjAyNjowNzowOSAxNzoyNzoxMAAALgENAAcAAAAAAAAAAIKaAAUAAAABAAADXoKdAAUAAAABAAAihogiAAMAAAABAAIAAIgnAAMAAAABAZAAAJAAAAcAAAAEMDIxMJADAAIAAAAUAAAilpAEAAIAAAAUAAAiqpEBAAcAAAAEAQIDAJECAAUAAAABAAAifpIBAAoAAAABAAADZpICAAUAAAABAAAijpIDAAoAAAABAAADTpIEAAoAAAABAAADVpIFAAUAAAABAAAidpIHAAMAAAABAAUAAJIIAAMAAAABAAEAAJIJAAMAAAABAAAAAJIKAAUAAAABAAADPpJ8AAcAAAAFAAAiDJJ8AAcAAAAEQQAAAJJ8AAcAAABkAAAiEpJ8AAcAAB6WAAADbpJ8AAcAAAAIAAAiBJKQAAIAAAAHAAAivpKRAAIAAAAHAAAixpKSAAIAAAAHAAAizqAAAAcAAAAEMDEwMKABAAMAAAABAAEAAKACAAQAAAABAAALuKADAAQAAAABAAAPoKAFAAQAAAABAAAi1qIXAAMAAAABAAIAAKMAAAcAAAABAwAAAKMBAAcAAAABAQAAAKQBAAMAAAABAAEAAKQCAAMAAAABAAAAAKQDAAMAAAABAAAAAKQEAAUAAAABAAADRqQFAAMAAAABABsAAKQGAAMAAAABAAAAAKQHAAMAAAABAAAAAKQIAAMAAAABAAAAAKQJAAMAAAABAAAAAKQKAAMAAAABAAAAAKQMAAMAAAABAAAAAAAAAAAAABUYAAAD6AAAAGQAAABkAAAAAAAAAAEAAAAAAAAACgF9eEA7msoAAASP3QAAJxAjKiMqMjAxODExMDgxNjAwOzstOzYAAwFBAAEBqGEAAIgHAABTcpkBmQE4/60AAAAA+2QCAAAAADs7LTs2AAMBQQABAahhAACIBwAAU3KZAZkBOP+tAAAAAPtkAgAAAAA7Oy07NgADAUEAAQGoYQAAiAcAAFNymQGZATj/rQAAAAD7ZAIAAAAAOzstOjYCAwFBAAEBqGEAAH8HAABScZsBmwE4/6gAAAAA+2QAAAAAADs7LTo1BAMAQQAAAahhAABkBwAAUnCbAZsBOP+mAAAAAPtkAAAAAAA7Oy05NQIDAEEAAAGoYQAAWwcAAFFumwGbATj/qAAAAAD7ZAAAAAAAOzstOTUEAwBCAAABqGEAAFMHAABQb5kBmQE4/6sAAAAA+2QAAAAAADs7LTk1AgMAQgAAAahhAAA4BwAAUG2ZAZkBOP+rAAAAAPtkAAAAAACIpSAANAGbAZkBAAEAAAEAAQAAAQAAAQABAAABAAABAAEAAAAAAOUAMxIVADI7OABcDAAA6AMuACsEAAAaCwsSGSBIU1NST05LSENAGw4KEBcfSlZVVFJQTUpFQRUQCREXGURXWFVUU1BMR0MdFwoQFxc6WVlXV1ZSTUlEIB0MDRgXOVxaW1pYU09JQx8bDw4YGUdbWlxbWFJPSUMXGxQOExdEW1tdW1lUT0lEHiEZDQ4WNFNZWVdUTU1IQx4nGA0KCy1TXl1bVl1NR0EkGxsOBg0mTVJSUVBOSUM8FRofCwwiNlVWS0JBOEA6MhUiFwcYKCVTWEQtSj46LyYaHQcQK0IlT1RQRUpAMyYdGwcJLjNsKkFMTEtGOiwfFwYHGVRZezg9Pj07OjMnHBUFDUBzdTsvMDAvLSolHxoVAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAEBAQEAAAAAAAAAAAAAAAABAQEBN1YAAAAAOwCgD7gLAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAiAcGBkAC/Pz8PNwAAEYAAAAAAAAAAAAAAAAAAAAAAAAGAIAAgAIAABAAfwCAAIIAggABAAAAAAAAAAAAAAAAAAEAAAAAAAAA9AEAALwAAABs////AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAHcBAAB3AQAAdwEAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAGAAAABQAAAAkAAAACAAAABQAAADAAAABAAAAAAgAAAAUAAAAwAAAAQAAAAHgAAACCAAAAAQAAAAEAAAByAQAA+gAAAHIBAAD6AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAACAwACBAQAeQB5AGQAZACrAFUAAAAAAZgGmP3Q/4P/EQVs/ysAhf1QBgABAAAAAQABAAAAAAAAAAABAQAAAAAAAAAAAAAAAAAAmgaX/c//gv8TBWv/KwCE/VEGAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAgACAAIAAgAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAgAAAASAAAAKAAAAEAAAABZAAAAcgAAAI0AAADFAAAA/gAAADYBAABqAQAAmQEAAOgBAAAqAgAAYQIAAI4CAAC2AgAA3AIAAP8CAAAfAwAAOwMAAE8DAABhAwAAcAMAAIwDAACiAwAAtwMAAMkDAADYAwAA5wMAAPQDAAD/AwAAEQBkHHAAqgAAdQsYIHAAAAEDBwsQFBkdIiYrLzQ4PUJGS09UWF1hZWpuc3d7f4SIjJGVmZ2hpamtsbW6vsHFys7S1tre4+fr7/P19/n7/f8EDBMaHyUpLjI2Oj1BREhMT1NXWl5iZmpucnZ6foKGio6Tl5ufo6err7O3u7/Dx8vP09fc4OTo7PD09vf5+/3/5gcKIAAAG0MANRsYOwBBADQAgHKlWlql/////0FXQgEAAE8FXwAAAOkD+QM2BfYDAAAAAHUFAADbAgAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAP8DQgX5AzwF/QMABAAAOwAAAeUDUQr+k1ML7XNXDOsjWw3os18Ou9NOGstTXBwAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAJYDEQAALwABFAgsAKcBCQAvAAEALwABACUAAQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAJkJ5iKlXAQAAAAAAEIF+QMAAAAAAAAAAAAA//8AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAA//8AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAO4QAAAAAAAA/f8AAAAAAAAAAAAAAAAAAAAAQgX5AwAAAAAsBAEELAQBBCwEAQRCBfkDAAAAAAAAAAAAAAAADwBIBXYB3gAHAAwAQgX5AwAAAgCwBkQEIggWAOORI4IjokiCRJJD8miyhJKEoojChOKokqiiqLK0wrTSqOKw8qMCxILIkt+i37Lfwt/S3+Lf8twCzBLIIswyxFLocuSC/5L/ov+y/8L/0v/i//L/AugS9CL/MuRC6FLkYuRyCJMMowizGMMU0x/jH/MfAx8THyMfMxxDGFMMYwRzBIMEkwijKLM/wz/TP+M/8z8DPxM/Iz8zLEMkU0SjX7Nfw1/TRPNIE0QjSDOE06TDBNTk1AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAOzstOzYAAwEUBBbjAwAAMzI2MDQwT1Y0OEIyUUFRTVRIRF9MVVhWSVNJT05TWgAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAA+EMAACgAeAEQJxAnABQAOwDLAAAQJxAnECcQJxAnECcAAAAAAAAAAJadsiYAAAAAAAAAAAAAAAAAAAAAKAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAArsgzAQCAAQAAAAAAAAAAAAAoAHgBAQAAAAAAAAAAAAAAAAQAAAAZAQEAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAEBS9wDAAAAS9wDGCEAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAgICAAAAAAAAAAAAAAAAAAAAAAAAAAAAAABaAAAAAgAAAAAAQCNBRmV4aTEHAAAGAABAAKkBKAMAAAAArQEAAAAAAAAAAAAAAAAAAEAAAAAtAwAAAAAAANABAABkArAB2ADYAKwC+AFIAEgAjAHYAIgCiAK0AAAAOAQ4BAAAAAAAAAAAAAAAAAAAAAAcAmgBaAFoAawC+AFIAEgAjAHYAIgCiAK0AAAAOAQ4BAAAAAAAAAAAAAAAAAAAAAAAANABAAAAAAAAQANAEQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAQMAQgACQgAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAMAGQDU/+n/DQBwAA4A8f+3/wAANwAwAPD/MQDc/wAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAQAAAPhBn6oBAGgsAQAYAAAAAAAAAAAAAABkAAAAuAugDwAAAAA4BKAFAAAAAAAAAABkArAB2ADYAAAAAAANAAAAAAAAAAAAAAAAAAAAAAAAAAEAAAAAAAAAAAAAAAAAAAAAAAAAZAAAAAAAAAAAAAAAnaoBAKT5CgCfqgEAH2sHAAAAAAAAAAAAXEQAAAAAAAAAAAAAAAAAAAAAAAAbQQAAG0EAABtBAAAbQQAAG0EAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAMUIxQjFCMUIxQgAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAACdqgEAkoMNAJ6qAQBKJwUAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAgAAAAbQGNAa0BzQHtAQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAOppAABOzgAAv5MAAIY/AQD/tQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAA5ZcAAOUrAQCY7AAAZ94BAMxJAQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAABAAAAAQAAAAEAAAABAAAAAQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAF84AACMcAAA3mAAABEOAQDAkQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAh20AAN/+AAAnlgAAQJoBAJ2pAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAACAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAiBMAAAAAAAAAAAAAAAAAAAAAAACIE4gTiBOIE4gTAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAABtAQAAAQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAABQAAABAAAABpAQAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAWHQe9fLo6vLZxPDzpMxy9N1RdvIjDZDwFtBy9EFJTvMzrdTzMSCi9z8FcvGoyajwAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAABySau8cQvfOzSPmzt31pK8WH3yut1zxjsUspO86E/Ju9qd3zvgKse8CIoDvEevBjwAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAPQAAAAAAAAAAABAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAjIyoqbWRlAEF1dG8AACMjIyMKAAAArsgzAQCAAQAAAAAAAAAAAAAAAAAAAAAAeAEAAP////////////////////////////////////////////////////////////////////////////////////8AAACpAAAAZAAAAF8AAABkAAAAtAAAAGQAAACpAAAAZDIwMjY6MDc6MDkgMTc6Mjc6MTAAMjAyNjowNzowOSAxNzoyNzoxMAAyOTE2NjgAADI5MTY2OAAAMjkxNjY4AAAAAgABAAIAAAAEUjk4AAACAAcAAAAEMDEwMAAAAAAACQEAAAMAAAABAYAAAAEBAAMAAAABAgAAAAEDAAMAAAABAAYAAAESAAMAAAABAAAAAAEaAAUAAAABAAAjZgEbAAUAAAABAAAjbgEoAAMAAAABAAIAAAIBAAQAAAABAAAjdgICAAQAAAABAABTtwAAAAAAAABIAAAAAQAAAEgAAAAB/9j/4AAQSkZJRgABAQAAAQABAAD/2wBDAAoHBwgHBgoICAgLCgoLDhgQDg0NDh0VFhEYIx8lJCIfIiEmKzcvJik0KSEiMEExNDk7Pj4+JS5ESUM8SDc9Pjv/2wBDAQoLCw4NDhwQEBw7KCIoOzs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozs7Ozv/wAARCAIAAYADASIAAhEBAxEB/8QAHwAAAQUBAQEBAQEAAAAAAAAAAAECAwQFBgcICQoL/8QAtRAAAgEDAwIEAwUFBAQAAAF9AQIDAAQRBRIhMUEGE1FhByJxFDKBkaEII0KxwRVS0fAkM2JyggkKFhcYGRolJicoKSo0NTY3ODk6Q0RFRkdISUpTVFVWV1hZWmNkZWZnaGlqc3R1dnd4eXqDhIWGh4iJipKTlJWWl5iZmqKjpKWmp6ipqrKztLW2t7i5usLDxMXGx8jJytLT1NXW19jZ2uHi4+Tl5ufo6erx8vP09fb3+Pn6/8QAHwEAAwEBAQEBAQEBAQAAAAAAAAECAwQFBgcICQoL/8QAtREAAgECBAQDBAcFBAQAAQJ3AAECAxEEBSExBhJBUQdhcRMiMoEIFEKRobHBCSMzUvAVYnLRChYkNOEl8RcYGRomJygpKjU2Nzg5OkNERUZHSElKU1RVVldYWVpjZGVmZ2hpanN0dXZ3eHl6goOEhYaHiImKkpOUlZaXmJmaoqOkpaanqKmqsrO0tba3uLm6wsPExcbHyMnK0tPU1dbX2Nna4uPk5ebn6Onq8vP09fb3+Pn6/9oADAMBAAIRAxEAPwDyrGMg/pTStSdOpzTSPSkIiKgj3qIgqcGpzSEBxg9aYiPAcYPDDof6VHjBwaeQVOKeu2XAc4bs3r9aBjIo3lcRxozu3AVRkn8K37DwZq13GZZIvsygEgScM3sF/wAcV1Xgy50mfT/LtLWO2vIFAnUnLP0G8E8kHjI7H6iui6VI0jkfD3hTSL+Ce2dHbUo23QiVvllA6rt7HjvV5YBCgjWMIF+UKBjAFWtTsZIpl1Cz3LNGwZtvXj+If1q80kWu2DalAoW6iA+1xD+L/poB79//ANeUBjeUChDLnPao7d2sLrcF3KeHUqCHXuDVzbz/AEpksIkTBHI6U7AV7u0jt5EkhOYJfnjY+ncH3HNMTk4Pardo6FGsrrcscjZUn+B+gP8AjUEkT28jxyDaynDc07AMCcg9cdePamTxfKSMgYqyoxnvSmMYwQPanYRlRp5TnIIVj9cGtfSpxbztbzOqQzkBmfojDO1s9hyQSegYnsKpzQ9QM/lRD+8Qow+ZRz7iiwHUBWVirqVYHBBGCDUiqrDBGQeoPeqlhcG6tFZ23TxYWTPVh2b+h9wCeWq6hzRYZnRltOvQwGQp7/xL/n+VPu7ZYLgrHgxsNyH/AGT/AJxVq8t/Ni3qPmT9RUUA+1WJg6yQAtH6le4/z7UxFPYKGXjIHSn4H50uBzVWEESh43QnkfMv9R/X8KRV9qVGMcit12nn3FSOgRyASVPIPqDRYBAoIwRmse4gEczrtwPp2raWqmoRZCSDHoaAM21wlwo5wRgmrc0eUB6AHmqbgryDj6cVpKRLEGH8Q6UCL9wftCW93yTPECxPdx8rfqP1qHaDTrA+Zp80R4aBxIvqVbCn9Qv50oA7UIZFtyPWprUcSpn7y5H1FMI5Ip1u2y4Q9s0xAR3qMrU8ihXZRn5SRUWAeaEBERhjz29KldQQhHTbimMeRx2qTOYlPoTQBGR1NRzLviYD04NSsMr9aZtHlkE9BSAw2GFPoeM5q8D8gPtxVJx8vP8AOrELfuVUenemkIktjtnibI+VgeT6Vs3WPtUoxj527e5rCRsYbg4rbvDi7lH+2TSe40Rduajm+7x3PrTi3FQzPhPxzRYZZRcWGPWT+lQ4GOn6VIrY05T6v3+lQ7uaLAeZPG0eQR/9amD/ADirxAZcEZ9vSqskJj6fdqBkZFMK1KBSEdcUgIiAwwetRHKnFTsOtNIDDB4NMCfT7+exuo7m2kMc8Ryjjv7H2IyPxxXpmi67b6zbmRAsUycSw7s7T7ex/wA+p8n5U81f0zU59Pu0uLdgsinBBJxIP7ppAj11Tn2I9Kyp0n0PUE1PT8BAQHToBnsR/dP6VNpOpw6nZLcwHj7rr3Ru4/8Ar9/zrQ4ZSrAFSCCOxFIorXVvBcW66jYDFrKcMneF/wC6fb0/zmljnFSQSv4fvWyjT6fc/LJGSenp1+8Oxq3eWYgZJIpPNtphvhlH8S+/uKYjLuIN67lHI6+4pwP22Ad7iFcD/pov+IqyFqtLG1vIs0J24OeOxpgV0HvUoHHNSXCK4+1RDCucSKP4G/wNRg//AFqpCGNFu/8A1VTdDE29R09a0iM+oqCVO9ICS0uPs063CLuUj5kJwGU9R/nOCAe1by44KtuUgFW9QelcxAfLYxt0Y8E9jW1pc25TaOeVy0Xv3Zf5kfj1JFAI00OKourWN4ssY4B3L9O4q2pouIhNCQBlxyv1oQypdRKku+P/AFUo3pj9R+H+FQ/hVm1xcW72uPnGXh+vcfj/AJ6VWBpoQEcZpy5aLHeP/wBBP+B/nQOmKRWET5YZHRh6imIcKJEEkLr6inFNjlTjg4ooAw3X1HTqPSp7FvlZCfunIp97HtkJ7Hmq0L+XOrEjB4NCA1dOYR6kkbE7J8xNj/a4H64P4VKEIJBHIqjJnAYdQeo7VqysspE4A2zDeMdieo/A5H4UAiuy4xTCMHjipm6f1qJvWmBZn+Zg4/jUH9P/AK1QEHP+FTqd9mh7o201A35CkgI2HXtToyTGw9MHFNfpzREw+YE9qYB1pO2PWkJFIGx0oAw5j8xz171JA48pee1Mu8LI+PU0y3f92Oc4oRLLK+3OPatrUDi+lGf4s1go/wB4+lbuqNjUZRkdvx4FD3Givnj9agnY4GPenFuO1V7hzxjp6/5+lAy/nFjGOmWJqAvweacz5tIfq2PzFQM+c9RSA4gA/WhlDqRUhTa5GOhxzzTcducn0qQKjxFDnqKbjirpQH3qtJCU+Ycj6dKVhkW3NRshqfHtSMv/AOqgCsQGBDdfWoyCpwasMnemEbvlI5oAv6Jq8+mXgmiIPGHQ9HX/AB969M0++hvrZLi3YmN+zcEH0PvXj5BU4Nbvh7XZNMuufmjfAkT++P8AEUAemyRx3ETRyqGRhgj/AD3qrp90umSNpeo5NjM26KXGTEf7w/qKltriK4hWWGQSRuMqw7//AF6fcW8d1AYpPqG/un1pDC5tJLWdoZB8w5BHRh2IPpUBjDAqRkHgipdMufMT+xtQdY5Y/wDj1lYgAZ/hJ9D2/wAinyQtG7I6lWU7WHoaAMuMiymZZFLwuMMPUf40k0JgkwDuRhuRv7wq5PCJEwevY+lV7fDA2c52Dd+7Y/wN/gaaERqfShlz7A0hV43Mci7WU4IqQYIwaoRSljxk4/MVLBKzYYFlkjIIYHByOhFSOmc/5zVf5opQ4GR3+lAHSQyrcwJcIAofIZR0Vh1A9u49jUisaydOu1gl+dh5EwAc9dvXDfh/InvWqQVYqwwynBHoaVhorXKNBOs8fGW3D2P/ANei7VGZbmP/AFc43Y9G7j/PrVmRBLEUPfocdDUFn+832UnAc5Qn+Fx/j0oQFYc0Mo707aVJDAgjjB7UhHBzVCHr+9Qf3k+U49Ox/pSEcUkDiOTnG1htPtTnGHI9DgigCtdRB4GOMkdOKypFBU/yrcwDkHoayJ4hHI6EcAnBoAmifzIst16GtGybzNOdcc27jH+42f5Ef+PVi2r7WdD35HvWlpcm3UViP3bgGI++en/j22m9hIs5qNu9KTjIPUHB9qaW+nSkhli1O6GePPO3cPwqJu9NspAl4gOME7Tn3olGx2U8MpxQBGSDmmRNiQZ5zQx5qENtlPIHvTESlqTPWmyH5mHvTQ3fNAGXenFxIB3ORVa3ceWct3PQ1Z1Di6btwKo25Lh8A8N6UIGXEbnpntW5qsgF+/PUKf8Ax0VzyOUbB4rY1S4Rbgu0i4KIQSRz8i0mESMOMHBBqvO/IA+gNUZtatojtQNIcfwjAP41mXOr3Fw3yKsYz65NK47HVu4FvCN3QEjn3/8ArVRmv7WDPmTxggcYOf0rmpru4nUCWd2AGMZ7df61WJVc4GSBipuOx2moeHotQ33GlqEusbntP+enqYj6/wCwfwJ6VyxVlJTBDA4II5B7jnpXo1xZAncP/riqd9pFnrUW2dxa6gBtS4b7s3oH9D7/AOSJiODxnkUhAOf61cv9Pu9NujbXcLRSLztbuPUHuKq7R37etUBWeIg5UfUCo8d/XrV3GTx3qJ4MklePapsMrEZ/ConSp8dR+lJjP0oArMobKt19aiIKHmrLp1phXcNpHSgDe8L+InsLhbacs9tIcMByVP8AeAx1x1HcfhXokbq6K6OrIygqynIIPQ14vgoefzrrvCfigWjLYX8n+jsTtkbJ8o9c8A/Ke47dR3BAO2vbNbyLAwsi/cb+n0qaxuX1aM21wCNRgXCsf+W6jsf9ofrT8YOP5VSvrRpStxAStxGQVKnGcHj8RSGTMOtVLm38xcqBvH6itGG5XV7VrlQFu4xm4iH8Q/vgfzqBhxQBUX/TYcZJuYl4/wCmij+oqFSOvWpZkaOQTxZVgckjsfWnyqs0X2uJQATiVB/Ax/oapCIiu5c9CKryxg8+tWBSOM5P50xFSF9v7p+54rbsZ/Ot9jH54FAJPdOg/LgfiPesSaMjlevXNS2l28TrPGF3pnKnow6EfQgkfjRuB0I5FVLhSknmrweufQ9jU4dSFeMkxuNyFuuPf3ByD7g0cOpU9DSGJc4mjW8UY8ziQf3X7/n1/Oqpqe1YRTyWkzYim+Un+6f4Wqu4eORo3BDKcEe9NANcDrUjOXRZCcn7rfUf4j+VM4YYpkLfvWhJ4fjJ7N2/w/GmA/cPaqmoJnbIPoam3UkqiWBk744+tAGK7mKVZMdDVrzMchsY6Edapz8ocj2NEMu6MZxxxTRJ0l6yySJdKBtuUEnHQMeGA+hBqDOabaP9o0hucvayY/4A/wD9kD/31SbvekhjXYxyqw69atXmDOXA4kUMMd8jn9c1Rn5TPoanSUSWcT8fJlC2fxH9aGBGxxxiq7yYlHHWm3ep2qsd0ylv7qcn9KxpNXkcAxwHPUlj1pXQ7G67ZK8feA/z+lNaRY13O6qPVjisGW/vZlz5vlqOAFqm7DerOzOcdSc0uYEjU1i5i83CSBjt+bBzz/8AqrMi1EQIwjTeG5Bbjt6VBLKvPljj3FVGZj1HSldjsi7LqE80ud6xjvgf5NQtOHQ72LnIwWOaqjPU5J9KcemOxqdwQplY52rimbiWx0pxRueOvtQsX978aYDCTuxSEEnbUmEBPPvmmlxyAOTzQI9qkjYjMhL/AO2eo+vr9ev1qjPa5HHWt+W1eFyjqVYdqrPbqeMYA9O30/z+VAHOz2tne2/2LUgwQf6mdeWiP09Pp+tcdq+iXWj3AWdQ0b/6qZOUcdsH19q9FubLpkDk8Ed6o+XGqSW13D59rL95CM7T6j/P4jrTQHm+0k9waMD9K6LW/C0lhG15YyG6sjzuXlo/r9PzHf1PPleODmqAglhDnPQ1AR2PH1q5jHTt6Ux4lYcH5uxpWAqMu6oiu4H1qwysvBppHFSMqkA5VvwNQkFGwatsgI4qIqCCrfnTEdn4O8UBxHpOoS4/htpWJ4OfuH0Hoe30Py9oQVJBBBU4II5FeKENGcGu68KeLPPSPTNRk/eKAkExB+cdArH16AHH1oA6O4jmtblb+zJSaPk47/57irZeG9tvttsoVc4miH/LJj/7Kex/CgmqDNJpV39st1BiYbZoj91lPUfQ/oaQydxVVGNnPvA3Rt8rIejL3U/0rQlETIs9u++CX7p7oe6t7j9etVHUMMNyDTASaERlWjJaGQbo29R6H3HeoxyDmnWsyxO1pcNiGQ5Dn+Buzf0NOkiaKRo5BtZTgimmIqyp1HtxVIt5L7ux4NaTjcuPyqhOuQSDg0wNLTLjefsuciQ7ov8Af9P+BAAfUL71eSSuWilIPllj7c10EN4byAXPWQnbN/v+v/AgM/UN2FAImvE3xeYOqdfpTJH+02yz9ZIwElPqP4W/p+Apwl4xmqvmCzuSWXfDIMMvqp/qKQ7Dg9RzHkOODQ6GORkJ3Yxgjow6g/lRwUKscAjk+lO4h8jb9swx+8HOOzDr/Q/jSK351UjvoIRJbzShe45zhh/jyPyqudZiyRDE0h9TwOtK47DNSjEUzHoGG4elZ9mxe5ZATh+ce9WL26uLyMbo44x2AyT9CaoPKyRiMsFyedg25PvijmsHLc3LK7hsLhhcSqkM8TI56kdwQO/zBaryaymCIomcgZBPAPvWOJFX7oAx0z61IJ3BBLAEZxjtSuCRZuL6+lBUkQqfQfzqnw6ETStIM9CeD/nNNkfdklj9CetRAnnqzDpikOxIZEBIVfrTXmcOTgIP1pFRvvEgH9fyoKJn5m780ARsxbpk1EVbOccDFTlkwMDp3NRtKACVPHtQBGUO3gD15ppj6npk9ulSeYAPlUseBzULLI2ecf1oEGIxzkMAcGmmQKNqjODSbEAOXH500yov3QzfpQAFiwpArZ6D86Fdn4C4z6UjK24h2P06UALtUZ3MM+gpGKL0GaTAIyB1/WpDbXCsVeGQHbnhSf8A9VAj3oSz6YvlXSvd6fn5WH+sg/xH6fSpZLZGhFxbyLNbv92Ven0I7H2rVkgwAeCGGQRyCP61l/Y57CZp9NZV3/623f8A1cg+namMqPGNpUjg9R2NZ08C7ip59Oea31WC/Dm1Vo5k5ltX++nuP7wrOuLMOPmUNjkcdKAMQI9pN5kYJU/eXOAwrF1vwsl0kmoaN8wzmS2xgqfYdvp0Pb0rqTA5Yp5bHHRsZB/+vVKWF4n82FijDuB29KBHmZBViCCpHUdKQjOcda9B1LQLTxBGZoCsGoIvzAj7+PXHUe45HfIrhryzuLC4a3uYjFIvY9x6g9xTAqsm4AHtVd0KkkZwOatc55ppGaBlPb6c1EycGrkseMsv4ioTjtSAqMARhuaiIKHB6dqtunGahKj7rdO1Ajs/CvisSomn6jJ8/SKZm6j0Yn9DXWOMggjPsa8bKmM+3Y123hfxP9oCaffP+84WGTH3u20+/oaAN+Cf+y7hkkVpLOfAdB1HuP8AaHb8qtzR+WRhg6MA0cg6OD3H+eKZNGskZVgCCORVK1uvsrmxumHkMSY5Ovlt6/T1H40iiWZPMXGeex9KktJjdxfZZD+/iH7onq4H8H1Hb8qSRWR2Rx8wPNV5o2P7yMlZEOQRwaVwsT1XuosrvXPT5sfzqwL63u4ftBkRJAcSg8ZP94fX+dV21S1TIUNL6hVzT5h2Me6yoyOCBxmrelXnlOJTkxSDZKo6geo9weR64x0NQTqJXYmMqOo3N0H4VFHcCLckbLEp/uDnr+fWj2iEoM6KZ0tnYSSIAP4t3B9CD3BHP41QutUhePbEjSv/AAnbgZ+prPaaNmBIyT/e5pDJjGDjHIAHSpUi+UsvqV20KIFRNmQrtycZzj+f51Xd5J2zNcMwJ6DgD8Khd0zwT0zz1qRSdhwvOKdxWGjyUmYAL/dz2/zzTfPJY9OvUDFOERIK5460gQIxVhhhQgEJZkJJJPNQPA3IwDVvdEhOPmAPUd/Wobiba2FQL79c5H/16dxWKoiOAcDHWkwinDNmiSZ3y7HaD1PQUxk8tA7uFGM5PGfpnr+FGoCl13cDNJuY8Ae3SonureM53Fzjoo96Y9+AcxREAdC3BoFcsGNs9MZ9aRou5bGenvVGS8lYY8zb9Krlt3Lkt7sc0CL8k1uhwZMn0HNQtdoCAsZb1zxUUcYkb5MueOFBP8q1msGW1FvbxgyPgyySDb6HAP19vWgDNhM905UeWgAz8xwP171EXEg+8xB/KtJNFk5aadVx2Rc/qf8ACoTaRK4DAtk85PX8qAM9ZV3bcBR6Gr1jYfbGLSZji/vY+99PyqcxRqdqKq+wFakIzbxemDk575NAEFrbi0VETa4VydxGCCR2/Kie3W7lHnBSuR0GCfx61ZKhctSKN0oPOAc9aBkEdhbRHiFenUjcam2joRj1qUKQQO2Oppkh2KeODxxQI9ukt7jTy32VBLAxy1u7YwfVT2pkUkV2jPCWyhw8bDDofcf1q9a6jb6hGUPySj+Enr9KqXti3mCeFzDOn3ZlHI9j6j2pgUruyjuNrZaOVOY5k4ZP8R7VXF6VlW31ILHKxwlyPuS/73off8/Wri3nziK/VIJW4SVeI5D7/wB0066tAytFNGCD1VhQBVltmRiCuDWfcWLMS0f3jyVPf8atxtPpq7NrXVmMny/+WkXup7j2q0FhuYBcW0qzQt0de3sR2NIDk57cht67kdDnjgqf6VHNb2uuWxtNRAEwP7qQfKT9D2Pt0NdJdWSzDPRh0YdfpXP39iVJWRQD+houBwOsaJd6PPsnXdGxOyVRwcevofas7HY9K9IS5S4iax1QiSFxtDyf+zHr9D2/lyuv+GLjSneeAGS0xnIOWjHv6j/aH4+pdwMEgNwfzqtLEUHAyD7VawDxj8aTp15pgUDTGXNWZoOdy9O/tUByDgjBFICsRgEMOP5VGQ0bfqDVllB7VERwQeRSA7Xw14mivoF0/UJljuEAEUzE4lH91v8Aa9D3+vXTuTvBj4Ppznn/ACa8yIaM/XoRXW6H4hN0gtbpma4AxHJ/f46H3/n/ADmd1qioWejN2Oa6WAQuyv5fCseCq/3fcdx9aryzSf8ALWUseh2jApQJGXJPI569KZIrO3A64LZ7msW2bqKIllBkD7Rk9CTnFCSsZsYAHYZpGUF25wo6e9KoVWZgcvnHWhJiuREMytucYUHk96ijTaXC5GeRjsPSrO0bGCYwB/WoerNsVsdqpRFzCJH+72/dYc8GpRGqgBmLEe9M2OBvbABpPMgVC7zxqNuQN2SfpWiRFyUsgOcA4phdixAHHpVOW/QEoiMcdT/hUDXcrJwgUZznniqRLZolmycZzjNRvJHEMyyKvU4Y479hWU0ssvDSuR6ZwPypiYA2qoLdcJkmgVzROoQAEIrP6YXr+dV5b5yDsiVSe7tk/pj+tRrY3kwGInVTk/Mdv41bj0R2YGaVQAeQhJLD68UAZz3Ejf8ALbac/wAA21BKOSR1Jz8xyTWvLpMMAAYs5x1Y9efamQRRIGTYu7PHHJHNAjNhtLuflIJCD90gYH59KtQ6HdSYLskfqDzj8q27Fy9vsbBMbY/A8/41Y2j/AOvQBjRaBCQTNLIzdRtwB/WrsWm2kf3bdSQT9/5v51cxz70v4Yp2AhKFCqrhQB0XjFSFeee9OK4X6Upxj36ZzQkFxgUdCOPesaf5ZCTxh/61tdBzWBqsnkysD/eJGD70xD8guM9fr0rShYiCMAZIXPpxk1ixszMCQcdfQmtm1nh8iMHhzn5fxzSYIUhy2CuPxyKdEPnA6Z5o+0uclYs+5b/Cod8pbcG28dgKkouYYHtjp1qOQgK298Dpk4FQFZXOfMkPHO08Go3sXlADyssefmUL19s/hQ2B6vIJInaOVGRl6qwwa0bPXCieVdbnA+645I9j6/zrfvbO2vo9lxHnHRgcMv0NcrqOj3VjukX97AOfMUfd+o7fXpVkGrMsN1BuXbJFIPqDVKKW4sE8oI1zbL0iJ/eJ/unv9DWRDfT2ZYxMMN95WGQf/r+9a1pfw6hEdvyyqPmjPX6j1H6j9aQy1G0VzB59u4lj7kDlT6MOxqlJbzW9w11YyCGY/fQj5JR/tD+tNdGguPPt5fJl6EgZ3ezDvTkvmnQmS38mQHswKN7juPoalspFiC7iu2MflmC5UcwMfve6HuPbrUVzbRXEZV8Af3vSqc6NcptkBH90r8pU+oPY1JJMx5nlIYAAHGScdyahspROd1DTZ0coEMvHDIMg/wCFGmxXlqDFcMPs/Oxd25kPsBng+ma1JXRicbnqrJIVAxwc8UubQrkOX1rwyJHe509ArfxQDADf7vp9On0rlSCpKspUg4IIr0cysAdp4+lZGs6MupASwgR3Cj7x6P8A73+NUpW3E49jjMY/KoZ4N3K9fTFWpYpraVop4mSQdQf5+4pnHHP4VoQZjZHXg01hkVeng80Ej71U2VkJVsgikIgIwMHpUZBjbrx2NWCN3NRsMcHkUAdJo2uyToLeVVeboCR98f4/zrT+0M5+U46DA78Yrg/mjYEEjByCKsTajeOCVuZAuPmCnH8qnlRSmzr3mRFYyyqgA5LsB/nmqjaxYRsczGXrxGMjP1rkQXkJ+85/M1dg028kQOsRCkkBiQASP/1j86dg5mbba8uR5dtxjne39KhfVbmY43JEM5AjHT86hi0mbGZJFz6qCf51ct9IiCF8tJt+VgTgc9D+P86YrlckyxO8s+dmMKzdcnHA/P8AKoEJZuFIH0rcisol5WFAcddtQ3MG7IPXPegCGKzjljdVkYygA8gBcZ/PitB7O0aPZHAUGeoc5PXGaoWsxjkVyC2z7wz1Hf8Az61tqqOMqQwPIYdx/T6UWGUU021VwfIUnHfJ5q0kaqAFUKPQDAp2OvP40o5GcU7CE28cduaepx0oHpxxSAgEgmnYRFdR+ZCT3UZrBlZ0udkaliw5A9K6QvGFxKwAI7nrWYti73TyLtAJ2hiP4f8A9dILXKum3jQ6j9mmUp5o2gnoxzwPz/nWzzk5x7CoDbhE5IPPOVzz681GFUBz5JbB4LN161NyuUnkuIkHDhj2C80LdQsOCx9gppsZAAxGq8Zx6U7A6A4wefrTuHKOMwK/KjtjkZGBUa3DKoJiXI9Gz/SpliB659MetPWBASRzmi4WKnmyMenH0qJrKOeRpJIQ7t1Lc4+npWqsK4ztp6RDHPTPpSCxkfYk3FihxnIG48VMlphciP65rQaPaMHHA7evNNK5TG4cdQaQ7FIQspIUYz0xxQIm3Z3E5q15e7gjIJ64qYQ4x0zmgZXWEDk9O9KY/QfTmrIQZ9aUjH9KBHtsoMa5DAj0Y/yNVPtS8kK/BIwRj/IpzLntUTJgVTZKRkX2kWdzIrrG0AzlkjICt+nH4VW/sq3gPyAEgY+YZP61suvtULx5HNTqVoZzQgEmQEnoQTnNCFUbJXp6CrMqDqMDH5mqbZB+bkZp2C4x5HbBfpVaVywIP4VI2Tnap/Ks66vrS2/193DFg9GcZpco7kmQAcnFQylT0BrJuvFOlw5EbS3J7eWmBn6nFZdx4wmYH7NZxpg8GRi36D/GlyoOY6NmKjKpjHbFV5i6ozyOEUdSzYArjrnxDqkwx9tMa56IAuOfXr39arR2N7qzqY4ZrksSFb5m/wAaOVBzG7qd7o88XlXV0khXlWiG5l+hHH4VzWVydrFlB+ViMEjscVPPpV3bFonRUlU4ZckFT75FWtM0WO6lH2i+MAIGNibs+oOehqrk7mbtznsajkhWVcMMHsRW/rPh+TTgbi1LT2ndv4o/97Hb3rH4A5575pp3FYyZInhO1x9DTCAVzWzJEhiKOdyt1x2+lZk1s0R4yV5wT6UCKhXHB6VGQUOR0NWCM1GRtB7g0AX7G+ZYvLIEiqOEPBH0NaNlewRSMMP5UmPMjI5HoQT3HP4HHeub+ZDkH8a2bFtPvIsTTyW1wPvFl3RkevHI4+v+ACN1ikeGDK6EZV16EdiKjW6W3uBKh3dnU9GHcH6//XqkLS8tovlDSQ84eGTzIz1zyMgdD+RqFprgDiMSLjqDwOKVmVdG99qVwGT7pGRnt7H3FRzASjcowQPzrFivnTIUDkj5TVyK8cruwP5Uhle43RSrggE/lVzSr4B/s0pPJzHnI2nuuOw7/XPrUWxJZDK4G4ggA9gasLGHBVWyc5IPPPr+NO4uUvMyg4z9B61EtygzjJDHggE1BDbHHzgLnqcc1aSBUYfNuA9adwsAl54zycA+tLsmVlBTIc4yOijrzViJIUyI1wT1CjFTrEW6ZAHQ4ouFiukCIefnI5BK9PWml2LFVU4xnIFXlsTwXZiOwqRLVV6KDn1pFJGWLZiAx3H8KkFttTJU/jxWqYgFweBTMp3xjtxSGZnk4c8cgcDFOERI6A9SeOtX3CHkE5qM46gHmgCARDkMQM/hT40UDjk96fxmlOM80AGAooVgOxx/OmFvmxmlBzQKwrbSDximoFCYBxQRwc+lNHfI49qBgSABg5PuaCwPT5vwoxk4A46GnhcUARh26hQOeKPnP3v5VKB7UuO5H5UWEep2ms21x8kw8huMZOVP49vxrRZAByK4ZXzTri+v0snhtryW3PVWTB2n8aLk2OvnKohZsKoGSTwBWBe+KNFsziW/jZv7sXzn9K8+m0nxDquopbs73pkJCM0vTAJ5DHA4B7//AF9mz+F+szgNcyQWuVztZ9xB9CF4/U1Qie8+INiM/Y7G4lPTMhEY+vc1g3XjfVLgMIkhtwQRlVLEfQmuytfhPpw5vdQnkJUcQqEw3fk54retfA3h2zcyR6akrZBHnu0mMemScUwPGZ9T1G/bZNdzzFzxGGOCR6KOM/hRBoeo3JAitXTfxvlGwfjk170tpYLA9mlrDHGeWhWMKOfYfzrmNR0DyWeSxk8xANwiY/OBznHqOPr9e6bBHBW3gK+dA093bwq65Hlgy8/oPyJq5a+C9NhZkv5pySR5coYLEfZuMrz36c/jW9b3j2jEDBRvvI3Q/wCBq7FcQ6gjxwhRMFO5HPsecY5AP/16m5SRljwxpltlI7FIZA28Pyzo3YgnP+FX4rkg+Ve7I5CflnA2xy/7w/hb36H9af8AZ761AEcYeFV/1RJ+X1Knt9DmnyeQ1o0kqShMZZDHyB7j9ahyRXKyrq2hW2qgpcKYLiMYWULyB6H1H+Qa4S/0u50i7eORVYqu7Cnh17Efl+Fd3aXuzMMcU89uDhVkGHi+hzyvtT50ttSiiElucI275nAK+v1B70uawcrOGjvrnSruSOaYGPcQFI6c4xn0qtfaOL2Fb/TLOaOOQbihChD/ALnPXqNvt2rc1rwrPfTSPBdJKg+Y7j875ycemc9+OtXtH0mLS7fybVpCnJlic9WIAyR2PyjGPfrmnzrdBys86KEEggjHUY6f4VG4UjBGQeteha34Zhu0eWF/Ju8HDZ4k46N/LNcHdWs9nO8NxE0bpwQf8f61cZJicWjLmtDHH5qHcgOD6iqhGc4raIwTzVO4siQZIVJHdR/SqIMxhimcocg1ORkdKjZcfSgRetL2cP5tvPJDKAMmNip9O3bmtG31KNj/AKdBJI5PM0bDcfXIPX8CK55GML7lNakRPlB9jLggEY+6e3Xt/wDqpbDWptjRzqmmS3um4kaAjdGOHIOc8ZODx3644qnabHgGOvtU+h38+l3q3MX3ekiZ4kXuOvXuD2IrW12yhg1OO/tGzaX48wZBwHPP4buuDzw1JstIzEj3Z44NXLaLIIx09vwpNvJJx64q9ZooTPfNSi7DUh3/ACk7u3HapRbANz0qwp4p31xTELHFGBkqPyqynA6Cqyn3qRXP1pgTeYQcY4pN3qRio+p5pHOPrQIHbj1FR544FBLd6TBzzSGLwR05pvXnPWnEkZ71G3JJPQUxCEg/L3peApxTeMYxSBvoaQx2B3pc46VGXJJIpyktxmgQ7qetHXj9KMEccYpucsQOooAeABnGOOtOGDj+tRhuAeKeDmmhDwBigD2oX+VO6DGKYjooponPXymAA+fkNz6447dffkVMzMAFkXg9M/XHX8KzNsi/dO8ejcH86khuXjyinGf+Wbj6c4/LkUhFpUUSbl/Wtqx166tgEc+dGOArdR9DWEJonOR+7PPB5H4d/wA/zqTcUOGGD2PY0rjO7s9Ttb0Yikw2fuNw3/16t156kpByDjHQjtWzp/iGeACO4HnIBwc/MPx71XMKx0zxpJ1HzDoRwRVSXyVUCVlljPBPBODxyD25oiu4b2NmgmUgAbs8FfqKrSWqmbzMEuB98cnGen9alyGkZ2vRaTNAZDFM1wzfK0KBmJ9xkZHHU/nWIvhe4Mpna5aF0OYmjJBT/az6/wD6q6hrZNxIj56En05NMNmIwSj7VzkkHv7/AK1m2y0kQKlwLdY5HEhHDO3Bb344zTJYFKMHwo74OP8A9VSTXLw5BIfGPw61TuLpcEjPYAjpUNXKWhA22Fd6lVJABbAzxnFUp51Xadvy8f4j/PtRLKJHw23IJH4/5FUnmQMVbhWONw5/zxS5S7ls7EDMnAbqo6jj/wDVVaW42SOQp3ck471H9pCggYDdSBVaaUFi+OT6knH+eKpRFcsJdeYGDOcgdScDGew7VA+mWOqxXMM65MSkxyK2Cjk9v146fjVYSmOQkcBhtPHatGwmTyLh+5CjdjGOG/WritSJPQ4HVNMm0+co+XGSAwHp61nZPTnB7Cuz1XYytFkEYJ5HXHH5f41x7mN5HCqwKk7lznGMd/xFbXMipc23mZkjHzdSP71ZzDrW2iu7YjiZyemASajl05rpwNyRSnpvYLu6ADHbr3xQIzbJkjuVLqHU/KVbODkjjir0dsEt3I3GMYGMcDrxn14NZ6I8F0EmQoythlYYwc961423bUBOzIJC57Z55+p/OkxodARggnB6Cus+xb/BpeWSKQ27meLaTlFzkg+5Bb8656C3It3dZON3I2+4xzXS2Vw8fhGYbUZUukQKy5BBdMk+/wAx/IUlYoyViYqDj5fWrcO5Vxjgcj3pIowqBVGAvT2qRR6846ZqSyQE8rTxknmmqvGcdaUE/wAPU0wHqMjINLyOKdEvGTnPpTiAQcUxEe5/Wl7c9aRenelHuaQCcbsHjNKNuOtMk4TJPTpUBmwvTr3ouBOzZJOe1Rbucdc0iudgGOcUg+8Rg5oGO6Hr+FNOSpwcUEkZFND5NIBM7RinqxzjOcc0mQVyeKFKL0PzY9OlAh5Lj5h0HWpADjjjmo/tQIIZefYU0XMag5yCfWmIlwMmkV857UwygqdoLHPSm8gknjJ6e1AFhXHQc05nwAagiIBCjJz6Cpiu5cBgD6Z5p3EbooKq64Ybh6GlAooJIjG4JKtuH91j/X/PWhLh4m2gltzZ8txweP8A6/b8+KkprAMpDAEHqCKBjorkM21tsUmBhN2QR0Jz2/8Ar9asCXbjcCtUGjOPlOQf4W/xqSKUqdhyoJwFboe/+NJjRpw3LRuHRyrDoQcGtu08Q7sJdjdyf3gHI+oFYdta/aEDD5QcnOffGKilTyJmj3btuOelS0M6e51yxhXP2lSSN3PBA+nHoayrjxLE4ZQ529yo5Fc1ql0+IoeMAFs455J7/gKoqXcD+VIpI35tajYkKSxJHLcD8qqSauwOV5OP/wBVZuwkEZpfL45JpDLE98WXG0qfeqxujg49O9K6gjnt70KqYzjtwPSmBH50mc8/nThll5PSlwMn/OaXGeM5x60ARNv24AGfer9kSVkTJO4Dj86qgdc9e1XLGIyOyg44/IfXNOwmZl8Pk27docAAnPX/ACDXIaap/te7jAARc845/hrtb9ftCuRjcCeQoAGen061xumfPrl0rHYTuQAnBOCOP0NUQT3OmCSNpbdeOMoDx06r+vHvWbllVhtTaTzlASp9OeRXXRx5hckADgDA+tU7nTIZz5hT95nqp6+xoUhtGNN9j1CFFul8uSIbY5F5wB2PqPb8qrsptZPKcEO3ocjj0NbMegPufDLt4IyRg/hzU0mioLUpJkjG5XwTtOe1N2JSZDbh0tjGFByMZ6E/5xW5cK1r4dsIPLANzMZGHcrhiD+iVn+SVTAyTn5c9+a1tfCxajb2aBgtpahUbPUMcfp5Y/OkUZ6qGBye/IqRVPJqIs3UZ981LESVz1pFEgxt6/jQignGeaeoIH1pQ6xHJwfoOaYh+GU8jgd6RtvIzn0FRSXIKAhfmPbriokcEZyPXrRcRIy+WuA31xS9R3/Cmk7iMnn60vUYHWgZHMSq4yTmq5U4wTnnHFTlGlyvJ4xToLCUy4JKqMZJ7Z9vw/WpGMUbV3Z4H60wu3Ud+uKvS6ZPHhomDAjIOP8AOKjGmzsSMgA9/egCoSRjn5aYzBf4h9K1YtGXdh2JOcHdxipo7G3ChPLA+bJ9OlAXMgpIEBKMc5xxjpx/WlW2uSAfI4JGCT1roordQQoXYAODj29qkSAFiCRu+nf0p2Juc9HpV2wOWRcDrtzk+n5c/hV210WMcuxdgM5HTrWwbbK7xjkYC45b/OT+VKsGERgyMpIOQORRYLmeunxoxZFHrzzj6fpUUtpuwTxjp6/WtVkbaTtBwcYPBpnkfKRs3EccnOKdhXMuO1VJAu3jI4q80EYjRQvLcE+pqVbRuQFJHqcc1MtuIySXJ2n5e+38+lFgIAaWkFLVEBTSKdSUhjcdqkjXNNqaIZIoGadkNsYHfBP61m3TE3Mv++f51r26jy1/3RWLI3mSs/8AeYmh7AjJvQPtROMEopOO/wAoqINgkdu1T6iu3UZR/d2jp/siq4IzUGiJFzhs9znPrRggcnrzTdxHY0Fz6UAAByScnnvSrnHP05FABIzupTlVIxx6mgBhOAflJpwIwP50hYsgGenr3pRt8s9Dg9vWgBdwxyRx610GgRI+nXbyrvBbGOp4Xt+dcw6CSZHZzlOgB47f4fz9a67w1n+y5iMqfPIBx/sr0qo7ky2MzU7dAXkiAXAPAO5SAMnPH0/SuC0pYm1u/dtm6OeQDJ5GWP8Ah+VelXkSqJzvdmZQNrYAHbsPTArh9P8ADlxLcXV7hCDLJtb+IZZuv4emapklo/KMFsA/qfWogwB9vUGrk2nvFCNzBzznA5HP/wBeo2gMWAycnms2aIiVWC5Gc+pp/mSH73ap4LS6uMmKIsB7YGM1bj0ed1yZN6Ac7FPGRx2+tAyrpsTzaraqF3fvlJx2AOT/ACpNVE1xrl9JhmVZFRcLnC7AcfmTWzpWm/Zr6OcMWMQbJ7cgipNPt0VZcnJkldsE9fnY/wCFNbE9Tm4rWWeZY1Qjd0LcAfWr8GjyAkbhnjtkd8j+VbLx4kKiNQcY5HQVJCrIUXBJxx6YJpWC5mxaMH++ZWfBJAYDHtip5PDsCFSRIw54555HU8c4J/KteIbU8wrg4z2JI55/z61OzfNwTtHt3Hp696pIVzMi0a0RTstoWbBOCvOTzzUd1p0E0ZBhUq3CkKM+36VsgYKgKQo570xkD4LLzjOByO+KdhXOcbRbURHAZSpzkdTkcdfpmmtpaxbgqggc5znj6/pW66kSsp/hXOVGSBn/AOuR/wDrqk4MqJ8wXg7+CM9PzpWHczEt2BJUbcDk9OKkCZO4nHPPQ1ddfmGFHA44+9nt+HSkKKq7cMmeAAOpzQBXijDkgsAcEkk9fqaUIBwOD/Spljwu0sCpY4Gehxxk/jTShCBsHGPvY60ARvtPJDc9AOOaaigsqkEEKdv1qcRuVGEBAPXbU0FucFgnGCpBPBHemIiigYHGPmXBKsMfQVMkWCQEPTJ44/zzVwRknLZHqRxnHT+tOEfyEjHTjIzTsIp+SxZWHRuoz2we9SiAbRnK46fNVrYOhHA6UwIQQoXIbksOlOwFRoTggfKevr/npQIiqE+WSw5IU9T6/p+tWwgH8PU9aTYcdSe9FgIQqjA4AHJwKaihVwoxkdB2qfyuc5x+Gc0eWoLbQM5yfWgRjD1p1NFKDSEOpKKOaBiipY8h1wMjPP5GohUqk5KjrtJFIZswjbgHoAP61hRjc4U98CtkGVbJ/MYNIqHcR0zjnHtWVCv75OP4hQwRjajLnUrgkEYfHPtVZWz8w6VrPZxPdSOQWZmLHn3P+fwpYrZfNVSmVDZOMAn/ADxWb3NFsZp8xUDLExDHAJGB+dKY7t4gVg427jn69vWuhMQaNYzGCBgY2575/wAP1q3FEqABVIyTk53Y5/8ArfpTswucyun6iVz9ncKTzwAR9MnJxUlraMYyzxSFR7gZ/OumZSMk7ieuD39h+VUZomM2yMsqsdxBUA9Af58fjinYVzLj02WWfbwq5AyxGSD+n/66X7MsOCYwAMN8wxwD3x/+vmtOKAuyrl3ReA2OnsfTpVt4UHyuu8Yzhhlcf5GfqaVguYirFHM7qFdAdmccY6Dp+H5V0mlqRpinI3Ebs4PGVGOPpWJHp7GdkD/IeCF6gHt/nNdBZL5dqQM8Y6np8q/pVx3JlsZd1vZDvPIHJHTJ449uv5iotDTEc4I/5aEfXk1avseWfQ/rTdGQCKXA6yN/M1VhdDJVSnyMnfByMEEUGNJOGxgDI4/z9K2LrThMZZY3yz4OD04GKzflXIfcSPlyM+uM+9Q0NMu6XGgtGVVwWYryeuB/PrVg2iyZ+UhcbRknI6DpUemxMkXmbsgnBVcnrjH5c/nV77rhdvsCfWmkBAsIRXJA3NnkfjWXZxyNblxkfO2OgyN5rbZcIxJzwTjHXiqmnpm0UE9HYcf7xosBCEO0MTuz69e5/L/61TxWipu3HdxgfgeasrBH3B6Y6npUu0DHHHemkK4xVyuFYYzzg5NKF3YY5+mDxzSggYBxz0OKevSmIRV/OmNEApC/3cY6fj9alFFMCu8ZfI4BzwageJ+qIA55YNkjPtz0q9imsgZcHI9waVh3M37OA7OYycMflCZzn8unt61GbZkLGJmzGp78H3+uMVq7OSfU85oCDJ47YGegHpSsFzNe2DIzbGyDkHBBJBOOO/r1pEtBkYRguSQ2OQP/ANdae3jJ5Puc0mzkU7BcoxW6gr8p4PXAOT65+gqcRKDkLVjbxzTelOwDAp9aNueKdnAy3FLigBgUDOBSY9qfSUxEQQKeBj2FAQZzk5x6088UnbOQB79qAExzSFBycdetPA5+lJxQI54U4UgFLUAO7UlFFAxRU8CBp1Ynp8uPqR/hUK1Pa5N1t7fKf1P+FAGlOQlrMfUH9RisyDiYHHTOPyrRmO+wkP8AtEfk+P6VRgA8wk9ApoY0Qoj7/lIwO38qmmhIbKnJIBIxwSD/APWFWGZU75OPrTYY5JBuxgZI61FihluVllJf5FUd+M5xz/n1q+dhwSw+XOGODj1we1MEAAwOh65+uaeIE/uj/CqSERO7uG8oMwc4ySQAPb9f8mmLp67TuOXYhixJPPf8OKuIir0AHr707HrTsIjigSGPao6dSTyaiAJlY54A6Y/M5q2oxUfloiOCBzk5PaiwEdurNKz5yehJ/Dp+Oatx8QY9CR27cdqaigHAwOnSmidZrMzW/wA2c7QQRyCQRz05GKaEyjejnGe3Sm6Gc2Zb1Y067Od2famaD/yDl47/ANKYdDTIzjis3U7dCPtAOGHDDI5960wKJV3RkFd3tSAyLeVxBHJwREChzgDB98/T8q1NmSWB3Y6YIxVOCyK27RSEOmVwR9eccfT8quQqoiUKNu0Y7E0kMbKzGF/lIOD79qg07H2bPo7D1xzVpowc+hqlpf8AqZAR0mb+dMC/kYzgGjHPA696Wkz1piDqR6Z9KcMAUgob7tACnAGaKa5/d5A646qeOfSlU5GcY+tAC0UgpaAExRS0lMBtGKXvSUAJSUtJ+VICNSzj5kKYY8E9QCQD+OAfxp+KT+IUtABSH1oopgN5PSkxwRjORg+9LSMQqlicAcnPSgBCuAu07Qp6Y7elMjLvNMSwKBgqADpgc8/XP5VJkEZBGDSKoRduAO5x6nk/rQIwB7UopBS1AC0UClFAwHWrVkczqB2JB/Kqwq1p6Bbgt/e+b+Q/pQBYnj2Qs/mMyyMMKei/ePH1zUNsuZj6Y/rU9zlbWGM/eGP0FMsxl2P0o6giyIlGOM4p4GOlIKXNMY4UoFRiRfM8s8MRke4/pUgoAcKD04po4/xp3Y0wHY96Qg88jGKBR2pAJGxYtngYGOCD39aezlUACk+vIpq4OfvHjqP/AK1BdfLwNxI46E9PegRmXYeOE/unbBJO0A+/rUGgXcSWJjmbyWT7wl+UjgetXrl14AblhwDxnmnaepMDmRjtB6UAXUII4IP0NLjIqBN8UUCuql2cqzBQOMMQePoKnpiGYBXIPXpg05BgfU55pQKUAYpDGnp071QsJEHngMOJmz7cCtHoOCRj0rKtoJZNTuLl5QAp8tUC8nIUkk96ARobiw4LDPccU5VOMliTSgUtADXB2Njrjj60rdODj1oOMGkPK57UwFIyhHtQo4+tIuCuM0iZ288H3oAXkE4AJ9zilGe+OnQUgI3EU6gAppp2eabjmgApKU0lMBM0GjFJSAP0oNBpPWmAdqSj8aDQAlMfG3G7GSBnOKeaaQGx6g5FAC0dqBnvR2oA50U4UgpRUCFFLSUtMYoqzpxb52I+6H/9C4/lVYVe09g4LDoyqfzoES3wx5f4/wBKbZj75+gpL0/vlHov9TTrP7rf73+FLqUizSikpRTAdRSClpgKOacKaKcKAFoPAoozQBGuHBZtpwBgt64/+vUw+WJc54UZJpka4RlHbpz7e3NOH+pU4x8o+XGMfnzSQmZt8Bt+YAgA5zTtHjI0+Mbnz0J3kf1qPUmxby89EY/pVrSwBYx49KB9C2FxjknHTJJpwoopiClpKUUAGMjFVITi9uE7YRvzyP6CrdVM7dQYY5eIZP0P/wBlSAtClpBRnFMB
PRJ-0009 | Al Sabiyah | Building a staircase (Block - Sand - Cement ) | 2026-07-20 | 2026-07-22 | Closed | 600 | 600 | Al Jodood
PRJ-0010 | Al Sabiyah | AC Split installation | 2026-07-20 | 2026-07-22 | Closed | 300 | 300 | Al Jodood
PRJ-0011 | Al Sabiyah | excavation & install cable | 2026-07-20 | 2026-07-20 | Closed | 500 | 500 | Al Jodood
PRJ-0012 | Al Sabiyah | (Tim ) meeting room | 2026-07-21 | 2026-07-21 | Closed | 400 | 400 | Al Jodood
PRJ-0013 | Al Sabiyah | 20x10 (approximate) shaded area between office and core shed ¦ Closed: under process | 2026-08-24 |  | Closed | 15200 | 15200 | AL Jodood
PRJ-0014 | Al Sabiyah | Outside water hook up with hose reels ¦ Closed: finish | 2026-08-24 |  | Closed | 1650 | 1650 | Al Jodood
PRJ-0015 | Al Sabiyah | Lighting under covered area (as necessary after completion) | 2026-08-24 |  | In Progress | 0 | 0 | Al Jodood
PRJ-0016 | Al Sabiyah | waterproof electrical covering for electrical box (see photos). | 2026-08-24 |  | In Progress | 0 | 0 | Al Jodood
PRJ-0017 | Al Sabiyah | x2 portable AC water units ¦ Closed: finish | 2026-08-24 |  | Closed | 4600 | 4600 | Al Jodood
PRJ-0018 | Al Sabiyah | x50 trestles (see photos) ¦ Closed: under porcess | 2026-08-24 |  | Closed | 9500 | 9500 | Al Jodood
PRJ-0019 | Al Sabiyah | x300 tabletop stabilizers (see photos) ¦ Closed: under porcess | 2026-08-24 |  | Closed | 6000 | 6000 | Al Jodood
PRJ-0020 | Al Sabiyah | Open new door from the main office to outside | 2026-08-24 |  | In Progress | 0 | 0 | Al Jodood
PRJ-0021 | Al Sabiyah | 9x9m common shaded area ¦ Closed: finish | 2026-08-24 |  | Closed | 12150 | 12150 | Al Jodood
PRJ-0022 | Al Sabiyah | Additional container module with 2 rooms. ¦ Closed: finish | 2026-08-24 |  | Closed | 9306 | 9306 | Al Jodood
PRJ-0023 | Al Sabiyah | Additional water storage container installed | 2026-08-24 |  | In Progress | 0 | 0 | Al jodood

## Purchases
ID | Type | Reference ID | Item Name | Quantity | Unit Cost | Total Cost | Supplier | Purchase Date | Notes
PUR-1784468110653 | Work Order | WO0002 | connector | 1 | 25 | 25 | Company | Company | 2026-07-05 | change the connector
PUR-1784468438717 | Work Order | WO-0012 | pump for desert cooler | 1 | 160 | 160 | Al Jodood | Contractor | 2026-07-07 | replaced the pump (new)
PUR-1784470108873 | Development Project | PRJ-0007 | Cable 6mm with Clips for 3Pcs- AC | 50 | 17 | 850 | Al Jodood | Contractor | 2026-07-10 | to connect the A/C
PUR-1784470155034 | Development Project | PRJ-0007 | AC Switch with Box & Bolts | 3 | 45 | 135 | Al Jodood | Contractor | 2026-07-10 | to connect the A/C
PUR-1784470259903 | Development Project | PRJ-0006 | Emergency Light | 7 | 100 | 700 | Al Jodood | Contractor | 2026-07-11 | to add new emergency light
PUR-1784470338664 | Development Project | PRJ-0006 | Cable 3x4mm with Clips for Emergency Light including installation | 7 | 95 | 665 | Al Jodood | Contractor | 2026-07-11 | to install the emergency light and connect with electric
PUR-1784472787083 | Work Order | WO-0015 | existing Water pump | 1 | 475 | 475 | Al Jodood | Contractor | 2026-07-08 | replaced new water pump
PUR-1784474264366 | Work Order | WO-0017 | Electrical Breaker | 1 | 45 | 45 | Al Jodood | Contractor | 2026-07-08 | replaced
PUR-1784474440405 | Work Order | WO-0007 | Feron for A/C |  | 0 | 0 | Al Jodood | Contractor | 2026-07-05 | add feron
PUR-1784474985681 | Development Project | PRJ-0008 | Cable 3x4mm with Clips - Socket with Box - Condute | 1 | 125 | 125 | Al Jodood | Contractor | 2026-07-10 | assembly done
PUR-1785315379619 | Development Project | PRJ-0009 | Block - Sand - Cement | 1 | 500 | 500 | Al Jodood | Contractor | 2026-07-20 | Building a staircase for cabin
PUR-1785316935134 | Work Order | WO-0019 | sensor A/C | 1 | 135 | 135 | Al Jodood | Contractor | 2026-07-19 | replace the new sensor
PUR-1785317000169 | Work Order | WO-0022 | feron | 1 | 120 | 120 | Al Jodood | Contractor | 2026-07-19 | add feron
PUR-1785317047997 | Work Order | WO-0021 | door lock |  | 0 | 0 | Al Jodood | Contractor | 2026-07-19 | replaced the door lock
PUR-1785321035270 | Development Project | PRJ-0012 | Extension room with 4 outlet | 2 | 105 | 210 | Al Jodood | Contractor | 2026-07-21 | new item
PUR-1785321154974 | Development Project | PRJ-0012 | cable 4x3mm | 12 | 8 | 96 | Al Jodood | Contractor | 2026-07-21
PUR-1785321534149 | Work Order | WO-0025 | Acid | 3 | 15 | 45 | Al Jodood | Contractor | 2026-07-26 | Acid 3 pcs to clean the pipe
PUR-1785327446580 | Work Order | WO-0028 | Shower Mixer | 1 | 16 | 16 | Company | Company | 2026-07-29 | replaced new
PUR-1785327574450 | Work Order | WO-0027 | Complete hand bidet set | 1 | 24 | 24 | Company | Company | 2026-07-29 | replaced new
PUR-1785327641629 | Work Order | WO-0026 | Washbasin faucet | 1 | 33 | 33 | Company | Company | 2026-07-29 | replaced new
PUR-1785423825814 | Work Order | WO-0020 | Toilet Fan | 1 | 60 | 60 | Al Jodood | Contractor | 2026-07-29 | new fan
PUR-1785423934533 | Work Order | WO-0021 | aluminum door lock | 1 | 38 | 38 | Al Jodood | Contractor | 2026-07-19 | re assembly
PUR-1785424329772 | Work Order | WO-0023 | socket | 3 | 18 | 54 | Al Jodood | Contractor | 2026-07-29
PUR-1785424397834 | Work Order | WO-0024 | A/C switch | 1 | 25 | 25 | Al Jodood | Contractor | 2026-07-29
PUR-1785426766370 | Work Order | WO-0030 | light | 3 | 24 | 72 | Al Jodood | Contractor | 2026-07-29 | replaced the old 3 pcs
PUR-1785426905213 | Work Order | WO-0031 | Socket | 1 | 18 | 18 | Al Jodood | Contractor | 2026-07-29
PUR-1785426950867 | Work Order | WO-0031 | Oven plug | 1 | 15 | 15 | Al Jodood | Contractor | 2026-07-28
PUR-1785427186987 | Work Order | WO-0032 | fan | 1 | 70 | 70 | Al Jodood | Contractor | 2026-07-29
PUR-1785427233882 | Work Order | WO-0033 | Paint + Sanding Paper | 1 | 25 | 25 | Al Jodood | Contractor | 2026-07-29
PUR-1785432307712 | Work Order | WO-0034 | bolt | 4 | 15 | 60 | Al Jodood | Contractor | 2026-07-28
PUR-1785497906300 | Work Order | WO-0034 | Shower head | 1 | 30 | 30 | Company | Company | 2026-07-31
PUR-1785497989135 | Work Order | WO-0035 | spray water hand | 1 | 25 | 25 | Company | Company | 2026-07-31 | replaced new
PUR-1786346201814 | Work Order | WO-0056 | spray water (bathroom) | 1 | 10 | 10 | Company | Company | 2026-08-09 | fixed, done
PUR-1786346882934 | Work Order | WO-0037 | socket & Switch | 2 | 22 | 44 | Al Jodood | Contractor | 2026-07-30 | new socket & switch
PUR-1786347060179 | Work Order | WO-0038 | flood light 200 wat | 1 | 130 | 130 | Al Jodood | Contractor | 2026-07-30 | new flood light
PUR-1786347977978 | Work Order | WO-0036 | feron | 2 | 150 | 300 | Al Jodood | Contractor | 2026-07-30 | feron for 2 pcs A/C Spilt
PUR-1786348135019 | Work Order | WO-0046 | fan | 1 | 75 | 75 | Al Jodood | Contractor | 2026-08-08 | new fan
PUR-1786348304390 | Work Order | WO-0047 | mixer | 1 | 115 | 115 | Al Jodood | Contractor | 2026-08-08 | new mixer
PUR-1786348694052 | Work Order | WO-0057 | light | 1 | 15 | 15 | Al Jodood | Contractor | 2026-08-08 | new light
PUR-1786348845138 | Work Order | WO-0058 | A/C Switch1 | 1 | 35 | 35 | Al Jodood | Contractor | 2026-08-08 | new A/C Switch
PUR-1786349364347 | Work Order | WO-0059 | Water Flashing toilet | 1 | 85 | 85 | Al Jodood | Contractor | 2026-08-07 | new
PUR-1786509152105 | Work Order | WO-0050 | hoses | 1 | 12 | 12 |  | Company | 2026-08-11 | new hose
PUR-1786509194761 | Work Order | WO-0051 | Handle Shower Hose | 1 | 12 | 12 |  | Company | 2026-08-11 | handle shower hose
PUR-1786509304664 | Work Order | WO-0043 | handle spray | 1 | 20 | 20 |  | Company | 2026-08-11 | new handle spray
PUR-1786509372063 | Work Order | WO-0042 | handle spray | 1 | 20 | 20 |  | Company | 2026-08-11 | new handle spray
PUR-1786595620114 | Work Order | WO-0061 | Handle spray | 3 | 56 | 168 | Raghad Al OFQ | Contractor | 2026-08-13 | full kit
PUR-1786595671463 | Work Order | WO-0062 | shower handle | 1 | 140 | 140 | Raghad Al OFQ | Contractor | 2026-08-13 | full kit
PUR-1786595722842 | Work Order | WO-0063 | light 100 wat | 5 | 85 | 425 | Raghad Al OFQ | Contractor | 2026-08-13
PUR-1786595753775 | Work Order | WO-0064 | spot light size 20 | 4 | 75 | 300 | Raghad Al OFQ | Contractor | 2026-08-13
PUR-1786595796947 | Work Order | WO-0066 | Drain trap | 2 | 48 | 96 | Raghad Al OFQ | Contractor | 2026-08-13
PUR-1786595836264 | Work Order | WO-0067 | door handle | 1 | 120 | 120 | Raghad Al OFQ | Contractor | 2026-08-13
PUR-1786595871098 | Work Order | WO-0068 | Fan 30*30 | 1 | 180 | 180 | Raghad AL OFQ | Contractor | 2026-08-13
PUR-1786769166817 | Work Order | WO-0041 | white cement & adhesive | 1 | 125 | 125 | Al Jodood | Contractor | 2026-08-12
PUR-1786771982207 | Work Order | WO-0053 | water heater heard with bulf | 1 | 105 | 105 | Al Jodood | Contractor | 2026-08-12
PUR-1786773683750 | Work Order | WO-0052 | drain with pipe for toilet cabinet | 6 | 80 | 480 | Al Jodood | Contractor | 2026-08-12
PUR-1786795015172 | Work Order | WO-0073 | water pump timer | 1 | 140 | 140 | Al Jodood | Contractor | 2026-08-14
PUR-1787035014896 | Work Order | WO-0078 | led light | 4 | 10 | 40 | Al Jodood | Contractor | 2026-08-14
PUR-1787320266192 | Work Order | WO-0054 | celling light | 8 | 18 | 144 | Al Jodood | Contractor | 2026-08-18
PUR-1787320446383 | Work Order | WO-0069 | fan 30*30 | 1 | 75 | 75 | Al Jodood | Contractor | 2026-08-18 | to replace
PUR-1787817914963 | Work Order | WO-0075 | hinges for Almuinum | 3 | 55 | 165 | Al Jodood | Contractor | 2026-08-24 | for 2 doors
PUR-1787817979860 | Work Order | WO-0075 | Rubber for camera stand 40 cm | 2 | 16 | 32 | Al Jodood | Contractor | 2026-08-25
PUR-1787818040661 | Work Order | WO-0076 | iron chain to hold the doors | 2 | 65 | 130 | Al Jodood | Contractor | 2026-08-25
PUR-1787818096668 | Work Order | WO-0076 | circle hold with hand for chain | 2 | 85 | 170 | Al Jodood | Contractor | 2026-08-25
PUR-1787825104115 | Work Order | WO-0079 | main valve | 3 | 49 | 147 | Al Jodood | Contractor | 2026-08-24
PUR-1787825504890 | Work Order | WO-0082 | light 4 pcs | 4 | 19 | 76 | Al Jodood | Contractor | 2026-08-24
PUR-1787825587061 | Work Order | WO-0070 | bolt lock door with key for steel | 1 | 55 | 55 | Al Jodood | Contractor | 2026-08-24
PUR-1787826046477 | Work Order | WO-0055 | Feron | 2 | 100 | 200 | Al Jodood | Contractor | 2026-08-09
PUR-1787831869157 | Work Order | WO-0080 | Sink Mixer | 1 | 125 | 125 | Al Jodood | Contractor | 2026-08-24
PUR-1787832161240 | Work Order | WO-0081 | shower connector | 1 | 30 | 30 | Al Jodood | Contractor | 2026-08-27
PUR-1787843493871 | Work Order | WO-0086 | shower mixer | 2 | 130 | 260 | Al Jodood | Contractor | 2026-08-24
PUR-1787843855650 | Work Order | WO-0087 | aluminum door hand repair | 1 | 180 | 180 | Al Jodood | Contractor | 2026-08-24
PUR-1787844908582 | Work Order | WO-0089 | panel breaker 20 am | 1 | 48 | 48 | Al Jodood | Contractor | 2026-08-25
PUR-1787858316688 | Work Order | WO-0065 | spot light 8 | 7 | 65 | 455 | Raghad Al OFQ | Contractor | 2026-08-13
PUR-1787860094338 | Work Order | WO-0083 | repair 2 pcs | 2 | 170 | 340 | Raghad Al OFQ | Contractor | 2026-08-27
PUR-1787861167131 | Work Order | WO-0096 | Shower mixer | 1 | 240 | 240 | Raghad Al OFQ | Contractor | 2026-08-27
PUR-1787861224697 | Work Order | WO-0095 | Angle valve | 2 | 45 | 90 | Raghad Al OFQ | Contractor | 2026-08-27
PUR-1787861610578 | Work Order | WO-0094 | Arabic toilet flush | 1 | 180 | 180 | Raghad Al OFQ | Contractor | 2026-08-27
PUR-1787861715904 | Work Order | WO-0093 | Long outdoor LED strip light | 2 | 85 | 170 | Raghad Al OFQ | Contractor | 2026-08-27
PUR-1787861764748 | Work Order | WO-0092 | out side light | 3 | 75 | 225 | Raghad Al OFQ | Contractor | 2026-08-27
PUR-1787861886948 | Work Order | WO-0091 | light size 20 | 2 | 85 | 170 | Raghad Al OFQ | Contractor | 2026-08-27
PUR-1787861967015 | Work Order | WO-0090 | light size 7 | 5 | 50 | 250 | Raghad Al OFQ | Contractor | 2026-08-27